## Sheet1
"We Group 1 were assigned to do our project on the ICTAK Trainer Management System. Test plan creation, Test case preparation, Manual tets and Automation tests were all done based on the same website. Login, Invalid login and SignUp were done automatedly and everything went great. But by that time the website which we were provided stopped working because of some application and server error. So we couldn't complete automation testing. The website stopped working on a weekday. Since, majority of the team members are working professionals, we had planned to do the work on weekends but because of site issues we had to stop the tests there itself.But we had completed60% of the maven automation project.As per the advice of the mentor ,we decided to push the maven project in to GIT HUB and started the performance test of new website(http://64.227.132. 109/"
KKEMJULY2022_GROUP01 CONTRIBUTION TABLE
Sl No | Module Name | Tasks(Individual)
|  | Akhil | Karthika | Divya | Priyala | Treesa
1 | Functional Document | "1.Planing 2.Designed 2.content Writing. 3.Discuss to team mates |  |  |  | Created funtional document and added details regarding functional aspects of each project modules
2 | Sprint Backlog | "1.Planing 2.Designed 2.content Writing. 3.Final Discusion"
3 | Jira Project | 1.Creating jira project 2.Creating User Stories 3.Creating Task 4.Creating Bug 5.Updating status in Jira 6.sprint creating 7.Update Documents in jira | updating status in jira
4 | Test plan | "1.planning 2.Sample Test plan Sending 3.Designing 4.Content writing 5.Before final submission discuss to team mates | Took part in creating and editing test plan. Created the template for the test plan, table of contents page and introduction then contributed contents and edited in testing strategy, execution strategy, test management process along with other members. | Added content for the following: Test Design Process, Roles and Resposibilities, Defect trcking nd Reporting, Test Excecution Process, Schedules | Edited and added content for the following: Test Risk and Mitigstion factors Roles and Resposibilities Validation and Defect Management Test Metrics Tried to make the alignment appealing to the eyes of the viewer Made every page text to justified | Checked different test plan templates. Added Test Management Tool in Test Management Process. Edited contents in test plan module Test Environment and verified the alignment.
5 | Test Case | 1. Designed test case 2. Executed test case 3. Prepared documents 4. Designed Automation framework" 6.add scenarios to team project 7.updated jira 8.Discuss to friends before final submission | Created test cases for SignUp/Enroll page (SC_03) to Verify trainers can add, submit, view & edit their personal details in Enrollment Form. Total 20 test cases in which 15 positive and 5 negative | Created scenarios for Mail Confirmation after course allocated by admin , blocking dates in Trainer’s calendar and logout . Total test cases in which 5 positive and 3 negative | Created two scenarios for allocating trainer and viewing if the allocation is done or not. A total of 8 test cases was prepared out of which 7 passed and 1 failed. | Created scenarios for View Allocation and approval of Trainer Enrolled. A total of 12 test cases were created in which 9 passed and 3 failed.
6 | Manual Testing | 1.Executed test cases 2.update actual result 3.Update remarks for make the application better 4.Update scenarios 5.solve the Teamproject mistakes and spell mistake and also add points to the team project 6.Discuss to Team mates before final submission | For the SignUp/Enroll scenario (SC_03) manually tested all the test cases in which all passed the testing. So the trainer can submit their personal details such as Name, Email, Phone, Address, Highest Qualification, Skill Set, Current Company Name, Current Designation, ICTAK Courses Handling (Dropdown), Photo and can enter a password for the trainer profile. | Manual Testing done as trainer locating confirmation email after course allocation by admin and verify the ech Meeting Details .Checking Logout button is clickable from MyAllocation_Details page | Tested manually whether as an admin i was able to allocate the trainers with appropriate details so that the trainers can plan for the respective courses. Also found out that there was no file uploading option for schedule. | Manual testing was done as an admin and allocated trainers were searched based on trainer name, skill set, trainer type, course id. Search using trainer type was not found to be working. Checked if enroll form is sent to admin after trainer enrollment. Also tested if email is sent to trainer along with Id, Email, Password and Employment Type after admin approval. It was found that admin can approve trainer enrollment without assigning the type of employment.
7 | Bug Reporting | 1.Find Bug 2.Create Bug on JIRA 3.Create Bug Report Model for our Group project 4.
8 | Automation Testing | 1.Create automation Testing using maven and selenium 2.Create maven project of login page and login,invalid login 3collect signup page locating element and add to team project 4.create a task in jira for automation testing 5.update details in jira 6.Create final project | Created the automation script for the SignUp/ Enroll scenario. Automated the test scenarios using the created scripts. Couldn't complete the automation due to the website issues. | Mail confirmation and blocking dates in trainer's calender is the part of manual testig . Logout scenario couldn't complete using automation testing due to some website issues. |  | Elements were located but was not able add to project and complete automation due to website issues.
9 | Performance Testing | 1.Send useful links and vedios to Discord and whtsapp 2.using jmeter tested the whole website 3.using csv data config fetch credintiol from csv file 4.generate html report 5.create performance testing report 6.push to git hub | Using JMeter, tested the website OS:Windows 10 Browser: Google chrome internet connection: Keralavision broadband Generated HTML and CSV report for the same. | Performnce testing of website using Jmeter is done Generted HTML Report from Windows 10 using google chrome | Creaters and recorded the courses page of ICTAK website using HTTP Test Script Recorder. Also created an HTML report of the same. | Did performance testing using JMeter in Windows 11 machine. Also generated the html and csv report.
10 | Jmeter Report preparation | 1.create sample formate of performance testing report 2.send to team mates 3update and design the document 4.push to git | Update contents to report discuss about html report design the document
11 | Git Hub | 1.Create a git hub repo 2.push all reports and documents related ICTAK KKEMJULY2022_GROUP1 3Collaborate all team mates to repo 4.submitt all document