## ICTAK Group1
ICTAK TRAINER MANAGEMENT SYSTEM(GROUP1) Project summary Report(2022-23) Group members 1.AKHIL 2.KARTHIKA 3.DIVYA 4.TREESA 5.PRIYALA "We Group 1 were assigned to do our project on the ICTAK Trainer Management System. Test plan creation, Test case preparation, Manual tets and Automation tests were all done based on the same website. Login, Invalid login and SignUp were done automatedly and everything went great. But by that time the website which we were provided stopped working because of some application and server error. So we couldn't complete automation testing. The website stopped working on a weekday. Since, majority of the team members are working professionals, we had planned to do the work on weekends but because of site issues we had to stop the tests there itself.But we had completed60% of the maven automation project.As per the advice of the mentor ,we decided to push the maven project in to GIT HUB and started the performance test of new website(http://64.227.132. 109/"

## Summary
| Overall progress of the QA cycle(Ontime, delayed, Stopped) | On time
| Total number of test cases | 67
| Number of testers | 5
| Test cycle duration | 19 NOV 2022 TO 10 DEC 2022
Status for 02/11/2022
| Number of test cases planned | 20
Number of test cases executed
| Number of test cases executed overall | 25
Number of defects encountered today
Number of defect encountered so far
Number of critical defects- still open
Overall status
| Number of test cases planned | 67
| Number of test cases executed (A=automation,M=manuel) | M=67, A=37
| Number of test cases executed(%) (A=automation,M=manuel) | M=100%,A=60%
| Critical defects percentage | NA
ICTAK Trainer Management System Group1

## Detailed status
ICTAK Trainer Management System
Module | Scenarios | Sub Levels | Complexity | Responsible tester | Date of Execution (M=manual testing A=automation) | Status(Pass(P) /Fail(F)/blocked (b)/not executed(NA Manual | Status(Pass(P)/Fail(F)/blocked(b)/not executed(NE)) Automation | Defect ID- Brief description | Severity | Status
| Login Page | Admin Login | Complex | Akhil | 27/11/22(M) | Pass | pass
|  | Trainer Login | Complex | Akhil | 27/11/22(M) | pass | Pass
|  | Invalid Admin Login with invalid email and valid pw | Complex | Akhil | 27/11/22(M) | Pass | NE
|  | Invalid Admin Login with valid email and invalid pw | Medium | Akhil | 27/11/22(M) | PASS | NE
|  | Invalid Trainer Login with invalid email and valid pw | Complex | Akhil | 27/11/22(M) | PASS | pass
|  | Invalid Trainer Login with valid email and invalid pw | medium | Akhil | 27/11/22(M) | PASS | NE
|  | Admin Login entering only username without Password | Complex | Akhil | 27/11/22(M) | PASS | NE
|  | Trainer Login entering only username without Password | Complex | Akhil | 27/11/22(M) | PASS | NE
| Menu elements clickable or not | Verify Home menu button is clickable | Medium | Akhil | 27/11/22(M) | PASS | pass
|  | Verify Login menu button is clickable | Medium | Akhil | 27/11/22(M) | PASS | pass
|  | Verify Signup/enroll menu button is clickable | Medium | Akhil | 27/11/22(M) | PASS | pass
|  | Verify Social media icon Facebook is clickable | Medium | Akhil | 27/11/22(M) | FAIL | NE | ICTAK Trainer Management System Facebook page is not display by the system | Low | open
|  | Verify Social media icon Twitteris clickable | Medium | Akhil | 27/11/22(M) | FAIL | NE | ICTAK Trainer Management System Twitter page is not display by the system | low | open
|  | Verify Social media icon instagram is clickable | Medium | Akhil | 27/11/22(M) | FAIL | NE | ICTAK Trainer Management System Instagram page is not display by the system | Low | open
ICTAK Trainer Management System
Module | Scenarios | Sub Levels | Complexity | Responsible tester | Date of Execution (M=manual testing A=automation) | Status(Pass(P) /Fail(F)/blocked (b)/not executed(NA Manual | Status(Pass(P)/Fail(F)/blocked(b)/not executed(NE)) Automation | Defect ID- Brief description | Severity | Status
| SignUp/Enroll Page | Verify the Sign/Enroll button is clickable | Medium | Karthika | 27/11/22(M) | PASS | PASS
|  | Verify the Name text field in the Signup form | Medium | Karthika | 27/11/22(M) | PASS | PASS
|  | Verify the Email text field in the SignUp form | Medium | Karthika | 27/11/22(M) | PASS | PASS
|  | Verify the Mobile No. text field in the SignUp form | Medium | Karthika | 27/11/22(M) | PASS | PASS
|  | Verify the Address text field in the Signup form | Medium | Karthika | 27/11/22(M) | PASS | PASS
|  | Verify the Highest Qualification text field in the Signup form | Medium | Karthika | 27/11/22(M) | PASS | PASS
|  | Verify the skill set text field in the Signup form | Medium | Karthika | 27/11/22(M) | PASS | PASS
|  | Verify the Company Name text field in the Signup form | Medium | Karthika | 27/11/22(M) | PASS | PASS
|  | Verify the Current Designation text field in the Signup form | Medium | Karthika | 27/11/22(M) | PASS | PASS
|  | Verify the Your Photo field in the Signup form | Medium | Karthika | 27/11/22(M) | PASS | PASS
|  | Verify the Choose Courses drop down in the Signup form | Medium | Karthika | 27/11/22(M) | PASS | PASS
|  | Verify the Password text field in the Signup form | Medium | Karthika | 27/11/22(M) | PASS | NE
|  | Verify the Re-Type Password text field in the Signup form | Medium | Karthika | 27/11/22(M) | PASS | NE
|  | Sign Up Button Verification | Medium | Karthika | 27/11/22(M) | PASS | NE
Module | Scenarios | Sub Levels | Complexity | Responsible tester | Date of Execution (M=manual testing A=automation) | Status(Pass(P) /Fail(F)/blocked (b)/not executed(NA Manual | Status(Pass(P)/Fail(F)/blocked(b)/not executed(NE)) Automation | Defect ID- Brief description | Severity | Status
| ViewAllocation Page | Verify the admin can get the trainer details , while searching using name already present. | Medium | Treesa | 28/11/22(M) | PASS | NE
|  | Verify the admin cannot get the trainer details , while searching using name not present in the list. | Medium | Treesa | 28/11/22(M) | PASS | NE
|  | Verify the admin can get the trainer details , while searching using skill set present in the list. | Medium | Treesa | 28/11/22(M) | PASS | NE
|  | Verify the admin cannot get the trainer details , while searching using skill set not present in the list | Medium | Treesa | 28/11/22(M) | PASS | NE
|  | Verify the admin can get the trainer details , while searching using trainer type present in the list. | Medium | Treesa | 28/11/22(M) | FAIL | NE | Admin is not able to get the trainer details, while searching using trainer type present in the list. - IG20 | Medium | OPEN
|  | Verify the admin can get the trainer details , while searching using course Id present in the list. | medium | Treesa | 28/11/22(M) | PASS | NE
|  | Verify the admin can get the trainer details , while searching using course Id present in the list. | Medium | Treesa | 28/11/22(M) | PASS | NE
|  | Verify the admin cannot get the trainer details , while searching using course Id not present in the list. | Medium | Treesa | 28/11/22(M) | PASS | NE
| Trainer Enroll | Verify pagination is working in ViewAllocation page | Medium | Treesa | 28/11/22(M) | FAIL | NE | Pagination is not working in ViewAllocation page - IG21 | High | OPEN
|  | Verify whether the enroll form is sent to the admin for approval after trainer enrolment | Medium | Treesa | 28/11/22(M) | PASS | NE
|  | Verify whether email is sent to trainer when admin approves the trainer, after assigning the type of employement | Medium | Treesa | 28/11/22(M) | PASS | NE
|  | Verify whether the admin approves the trainer without assigning the type of employement | Medium | Treesa | 28/11/22(M) | FAIL | NE | The admin approves the trainer without assigning the type of employment - IG19 | High | OPEN

## Bug report
ICTAK Trainer Management System (Group1) BUG Report
Group members 1.Akhil 2.Treesa 3.Karthika 4.Divya 5.Priyala
Category | Label | Value
Bug ID | ID number | ICTAK-SC1-TC4
| Name | Facebook menu button - Unable to clickable facebook menu of ICTAK
| Reporter | AKHIL K
| Submit Date | 25/11/2022
Bug overview | Summary | ICTAK Trainer Management System Facebook page is not display When Clicking the Facebook menu of landing page
| URL | https://trainermanagement.herokuapp.com/
Screenshot
Environment | Platform | CHROME Version 107.0.5304.121 (Official Build) (64-bit)
| Operating System | Windows10
| Browser | Chrome 53
Bug details | Steps to reproduce | Step 1: Launch ICTAK Trainer Management System Website Step 2: Scroll down Step3.: Click on Facebook menu button Step 3: Verify the system navigates to the Facebook Social media page of ICTAK Trainer Management System
| Expected result | The system should display twitter page of ICTAK Trainer Management System
| Actual result | ICTAK Trainer Management System Twitter page is not display by the system
| Description | /
Bug tracking | Severity | Minor
| Assigned to | DEVELOPER
| Priority | Low
Notes | Notes | Improved Brand Awareness. Increasing our businesses visibility,Create good image about our companyespecially with the power of social media. .
Category | Label | Value
Bug ID | ID number | ICTAK-SC1-TC5
| Name | Twitter menu button - Unable to clickable Twitter menu of ICTAK
| Reporter | AKHIL K
| Submit Date | 25/11/2022
Bug overview | Summary | ICTAK Trainer Management System Facebook page is not display When Clicking the Twitter menu of landing page
| URL | https://trainermanagement.herokuapp.com/
Screenshot
Environment | Platform | CHROME Version 107.0.5304.121 (Official Build) (64-bit)
| Operating System | Windows10
| Browser | Chrome 53
Bug details | Steps to reproduce | Step 1: Launch ICTAK Trainer Management System Website Step 2: Scroll down Step3.: Click on Twitter menu button Step 3: Verify the system navigates to the Twitter Social media page of ICTAK Trainer Management System
| Expected result | The system should display Twitter page of ICTAK Trainer Management System
| Actual result | ICTAK Trainer Management System Twitter page is not display by the system
| Description | /
Bug tracking | Severity | Minor
| Assigned to | DEVELOPER
| Priority | Low
Notes | Notes | Improved Brand Awareness. Increasing our businesses visibility,Create good image about our companyespecially with the power of social media. .
Category | Label | Value
Bug ID | ID number | ICTAK-SC1-TC6
| Name | Twitter menu button - Unable to clickable Twitter menu of ICTAK
| Reporter | AKHIL K
| Submit Date | 25/11/2022
Bug overview | Summary | ICTAK Trainer Management System instagram page is not display When Clicking the instagram menu of landing page
| URL | https://trainermanagement.herokuapp.com/
Screenshot
Environment | Platform | CHROME Version 107.0.5304.121 (Official Build) (64-bit)
| Operating System | Windows10
| Browser | Chrome 53
Bug details | Steps to reproduce | Step 1: Launch ICTAK Trainer Management System Website Step 2: Scroll down Step3.: Click on instagram menu button Step 3: Verify the system navigates to the instagram Social media page of ICTAK Trainer Management System
| Expected result | The system should display instagram page of ICTAK Trainer Management System
| Actual result | ICTAK Trainer Management System instagram page is not display by the system
| Description | /
Bug tracking | Severity | Minor
| Assigned to | DEVELOPER
| Priority | Low
Notes | Notes | Improved Brand Awareness. Increasing our businesses visibility,Create good image about our companyespecially with the power of social media. .
Category | Label | Value
Bug ID | ID number | ICTAK_SC6_TC5
| Name | View Allocation page - Admin not able to find trainer details, while searching using trainer type
| Reporter | TREESA ANTONY
| Submit Date | 25/11/2022
Bug overview | Summary | In ICTAK Trainer Management System View Allocation page, trainer details are not provided to the admin, while searching using trainer type already present in the list
| URL | https://trainermanagement.herokuapp.com/
Screenshot
Environment | Platform | CHROME Version 107.0.5304.121 (Official Build) (64-bit)
| Operating System | Windows10
| Browser | Chrome 53
Bug details | Steps to reproduce | Step1. Go to url:https://trainermanagement.herokuapp.com/ Step2. Enter the Admin Username in username text field Step3. Enter the Admin Password in password text field Step4. Click Sign in button Step5. In the landing page, click on ViewAllocation Step6. In the searchbox type the Trainer Type
| Expected result | Trainer list is not displayed in ViewAllocation page
| Actual result | Trainer list should be displayed in ViewAllocation page while searching using trainer type
| Description | /
Bug tracking | Severity | Minor
| Assigned to | DEVELOPER
| Priority | Low
Notes | Notes
Category | Label | Value
Bug ID | ID number | ICTAK_SC6_TC9
| Name | View Allocation page - Pagination is not working
| Reporter | TREESA ANTONY
| Submit Date | 25/11/2022
Bug overview | Summary | In ICTAK Trainer Management System View Allocation page, pagination is not working
| URL | https://trainermanagement.herokuapp.com/
Screenshot
Environment | Platform | CHROME Version 107.0.5304.121 (Official Build) (64-bit)
| Operating System | Windows10
| Browser | Chrome 53
Bug details | Steps to reproduce | Step1. Go to url:https://trainermanagement.herokuapp.com/ Step2. Enter the Admin Username in username text field Step3. Enter the Admin Password in password text field Step4. Click Sign in button Step5. In the landing page, click on ViewAllocation
| Expected result | Pagination should be done for ViewAllocaton
| Actual result | Pagination should be present for ViewAllocaton page
| Description | /
Bug tracking | Severity | Minor
| Assigned to | DEVELOPER
| Priority | Low
Notes | Notes
Category | Label | Value
Bug ID | ID number | ICTAK_SC7_TC3
| Name | Home page - Admin approves the trainer without assigning the type of employement and email is sent to trainer
| Reporter | TREESA ANTONY
| Submit Date | 25/11/2022
Bug overview | Summary | In ICTAK Trainer Management System Home page, admin approves the trainer without assigning the type of employement and email is sent to trainer with Id, Email Id, Password and Employment Type as "undefined"
| URL | https://trainermanagement.herokuapp.com/
Screenshot
Environment | Platform | CHROME Version 107.0.5304.121 (Official Build) (64-bit)
| Operating System | Windows10
| Browser | Chrome 53
Bug details | Steps to reproduce | Step1. Go to url:https://trainermanagement.herokuapp.com/ Step2. Enter the Admin Username in username text field Step3. Enter the Admin Passwordin password text field Step4. Click Sign in button Step5. In the landing page, check for the trainer name. Step6. Click Approve button corresponding to the trainer.
| Expected result | Email is sent to the trainer with Id, Email Id, Password and Employment Type as "undefined"
| Actual result | Email should not be sent and trainer should not be approved
| Description | /
Bug tracking | Severity | Minor
| Assigned to | DEVELOPER
| Priority | Low
Notes | Notes